## Sheet1
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | BookTrade |  |  |  |  | Project Name: | BookTrade
National Center: |  |  | Sandy Homes |  |  |  |  | National Center: | Sandy Homes
Project Manager Name: |  |  | Noman Ahmed Khan |  |  |  |  | Project Manager Name: | Noman Ahmed Khan
Project Description: |  |  | Book E-commerce |  |  |  |  | Project Description: | Book E-commerce
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | Medium | Low | Green | Current project skill set may not be adequate to complete all project work. The current development team has only 3 Members working in this project | If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule and Time | The due date approaches for the completion of project but required processes and skills have not been identified | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Planning and aiming to find various resources and develop skills to complete the project before hand | Find resources that meets required skill set through external hiring sources.
| Open | High | Medium | Red | Various Information Risks and Security Such as copyright, trade secret and violations by web developers. Unauthorized access resulting in theft of customers private information. Credit card information disclosure or interception, used for fraudulent purposes | These information risks can cause great losses, can get the company fined and sued, loss of customers, reputation and other consquences | Website Reputation Legal Consequences Theft of vital Data Fradulent Transactions | Various problems will overshadow the project, Intruders will mess around with the website and the Web Administrator will have to take quick actions to minimize further damage | To protect further damage, everyone on the team needs to be reactive and act promptly | Mitigation | Safeguard the system immediately when fraudsters or intruders try to access the vital information resources in the system | Adopt best practises to prevent information risks from happening in the future by adopting latest technology, secure servers and strict rules
| Open | High | Low | Yellow | Transaction Risks and Viruses Since all the business transactions and deals are travelling through the web,. The presence of malicious softwares like virus, worms and Trojan horse can make your system a pray and cause damage | The business transactions can be compromised which will cause financial loss, identity theft and other issues | Financial Theft Identity Theft Virus Attacls | The different viruses that infect the system can spy on user data, crash the system, launch attacks and some other consequences | Unusual things start to happen with the website, information and financial value is compromised | Mitigation | Act immediately to deal with such viruses and remove them from your computer. Contact the service you are dealing with and let them know about the issue | Akways have a good anti-virus and keep it updated to impede against any such kind of attacks in the future
| Open | Medium | Medium | Yellow | Operational Risks Hosting issues where website suffers failure and store stays offline. Supplier issues when top-selling product is pulled off from the market. Example: Galaxy Note 7 | Website becomes unavailable, huge loss of revenue | Dependency of Website Reliability Customer Satisfaction | Unable to access the website, cannot find the products | Website stays down for hours with no information of its return. Product unavailable | Avoidance | Website should be Online soon without issue | Use backup services and alternative options to avoid such issues
| Open | Medium | Medium | Yellow | Unauthourized Access and Poor Safety Someone may access your data and account illegally, can be your employees or outsiders. Poor system configuration and poor encrypted transmission | Confidential business data will be lost by illegal measures of people | Business Data Customer Satisfaction Project Resources | Valuable and confidential business data may be leaked | Leaked information and theft of data | Avoidance | Prevent further leak and cybercrime help | Overall strong configuration of systems and strong encryprted transmission
| Open | Medium | Low | Green | Business Risks Unethical content in the website, defamatory statements, illegal promotion and contests, violating terms, intellectual property, change in supplier relationships, data access and ownership, unprotected domain names, incorrect integration | The business objectives and goals will be compromised | Stakeholders Sponsers Content Creators | Business issues such as liability, accountability and responsibility | Chaos regarding data ownership, access and other business issues | Mitigation | Communicate effectively to resolve issue | Define strong business rules, preferences and priorities for every stakeholder. Use of contracts and ethical behaviour. | fi
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.